## Simple Procurement Plan
Ministry | [Enter Name of Ministry] - Simple Procurement Plan - [Enter Year]
Planning | [9 empty] | Preparation | [7 empty] | Execution
Fund | Dept | Progr | Activity | Cost Centre | Description of Purchase | Contract Type | Procurement Type | Procurement Value | Cash Flow Endorsed By DG | Specifications Approved By CSU | Tender Documents Approved By CSU | Draft Contract Approved By CSU | Advertise Opening | Advertise Closing | Proposals Evaluation | Recommendation to DG | DG Approval | Notification of Award / Signing of Contract | End Date of Contract

## Simple Procurement Actual
Ministry | [Enter Name of Ministry] - Simple Procurement Actual - [Enter Year]
Planning | [9 empty] | Preparation | [7 empty] | Execution
Fund | Dept | Progr | Activity | Cost Centre | Description of Purchase | Contract Type | Procurement Type | Procurement Value | Cash Flow Endorsed By DG | Specifications Approved By CSU | Tender Documents Approved By CSU | Draft Contract Approved By CSU | Advertise Opening | Advertise Closing | Proposals Evaluation | Recommendation to DG | DG Approval | Notification of Award / Signing of Contract | LPO Number | End Date of Contract | Contract Status | Vendor | Vendor Evaluation | Comment

## Complex Procurement Plan
Ministry | [Enter Name of Ministry] - Complex Procurement - [Enter Year]
Planning | [9 empty] | Preparation
Fund | Dept | Progr | Activity | Cost Centre | Description of Purchase | Contract Type | Procurement Type | Procurement Value | Cash Flow Endorsed (DG F&EM) | TEPP Approved (CTB) | TEC Appointed | Tender Specifications Approved (CTB) | Tender Documents Approved (CTB) | Draft Contract Approved (Attorney General / CTB) | Advertise | Open Tenders | Evaluate Tenders / Proposals | Recommendation to COM | Ministers Submission | Tabled in COM by MoFT | COM Approval | Notification of Award
Note on J3: Project Plan and Cash Flow Project prepared and submitted to the Min F&EM. Funding endorsed Could be part of the TEPP
Note on K3: TEPP = Tender Evaluation and Probity Plan. Alternative Processes and International Advertising (as required) approved by CTB
Note on L3: By Chair CTB

## Complex Procurement Actual
Ministry | [Enter Name of Ministry] - Complex Procurement - [Enter Year]
Planning | [9 empty] | Preparation | [12 empty] | Execution
Fund | Dept | Progr | Activity | Cost Centre | Description of Purchase | Contract Type | Procurement Type | Procurement Value | Cash Flow Endorsed (DG F&EM) | TEPP Approved (CTB) | TEC Appointed | Tender Specifications Approved (CTB) | Tender Documents Approved (CTB) | Draft Contract Approved (Attorney General / CTB) | Advertise | Open Tenders | Evaluate Tenders / Proposals | Recommendation to COM | Ministers Submission | Tabled in COM by MoFT | COM Approval | Notification of Award | End Date of Contract | LPO Number | Contract Status | Vendor | Vendor Evaluation | Comment
Note on J3: Project Plan and Cash Flow Project prepared and submitted to the Min F&EM. Funding endorsed Could be part of the TEPP
Note on K3: TEPP = Tender Evaluation and Probity Plan. Alternative Processes and International Advertising (as required) approved by CTB
Note on L3: By Chair CTB
Note on AC69: phill: Exchange 26th Oct 2012

## Thresholds
Value | Description | Treatment
Less than 100,000 | Generic one off small items that can be done by RFQ | Can be captured in one line or left out
Greater than 100,000 and less than 1,000,000 | Periodic recurrent spending like electricity and fuel | Should be shown as standing order
Greater than 1,000,000 less than 10,000,000 | Simple procurement | Must be included
Greater than 10,000,000 | Complex procurement | Must be included

## Key
Fund | Contract Type | Procurement Method |  | Yes/No | Contract Status | Vendor Evaluation | Month
2 = Gov | Goods | SS | Sole Source (SS) | Yes | Not started | Poor | Jan
4 = Don | Services | RFQ | Request for Quotation (RFQ) | No | Ongoing | Satisfactory | Feb
| Works | RFT-S | Selective Tender (RFT-S) |  | Complete | Average | Mar
| Consultant Services | RFT-S | Open Tender (RFT) |  |  | Good | Apr
| Personnel | RFP | Request for Proposal (RFP) |  |  | Very good | May
| Minor | EOI | Expression of Interest (EOI) |  |  |  | Jun
| Mixed | SO | Standing Offer |  |  |  | Jul
| TBA | [5 empty] | Aug
Sep
Oct
Nov
Dec
PHASE | MILESTONE | WHO | WHEN?
Planning | Cash Flow Endorsed | DG MFEM | October
| TEPP Approved | CTB | October
| TEC Appointed | CTB | November
Preparation | Tender Specifications Approved | CTB | November
| Tender Documents Approved | CTB | November
| Draft Contract Approved | Att Gen DG MFEM | November
Issue / Receive | Advertise | PA | December
| Open Tenders | CTB | February
| Evaluate Tenders / Proposals | CTB | February
Evaluate / Approve | Recommendation to COM | CTB | February
| Ministers Submission | PA | February
| Tabled in COM by MFEM | MFEM | February
| COM Approval | COM | March
| Notification of Award | CTB | March
| Execution of Contract | PA | March
Note on B16: Project Plan and Cash Flow Project prepared and submitted to the Min F&EM. Funding endorsed Could be part of the TEPP
Note on B17: TEPP = Tender Evaluation and Probity Plan. Alternative Processes and International Advertising (as required) approved by CTB
Note on B18: By Chair CTB